## Sheet1
Project ID= 02
Project Name: Niyamat Express
Tested By : MD.Arman Ali
Date: 28-09-2024
| Module | Bug ID | Bug Description | Priority | Bug Screenshot | Browser
| Outer functonalities of ERP | 1 | Home page auto selected and do not get Automated | Medium | https://drive.google.com/file/d/1tICAeQo-4eSxgkHVWAVz1ru6JYekc5P-/view?usp=drive_link | Chrome
|  | 2 | Change the footer colour its cover our logo. | Medium | https://drive.google.com/file/d/15uIPVGw0pXoSGZ3TpUuVN7QZe2YHrLv8/view?usp=drive_link | Chrome
Keep distance between niyamat It and Niyamat unity aslo change colour.
| Login | 3 | In login module its working well but found some issue. In password box please use toggle to see the password for | High |  | Chrome
few second.Also added a notification fon successfull login and if user use worng password or email its must
show notification. Remove google login function.
| Booking(Online) | 4 | In Online Booking distric droup down function not working also area. please correct sender mobile number. | High | https://drive.google.com/file/d/1cS1jTjzj04ryyr9g9JR1uwRVgPWBVnEa/view?usp=drive_link | Chrome
| All Parcel List Offline | 5 | In All Parcel List Offline Function Receiver name mixupwith Your name. Please correction it. | High | https://drive.google.com/file/d/1iqfE3L566jpXz5QIRnkYCGQS4J8my9-1/view?usp=drive_link | Chrome
| All Parcel List Online | 6 | In All Parcel List Online Function Receiver name mixupwith Your name. Please correction it. | High | https://drive.google.com/file/d/18qk5N8kQCVCa2UTTlq6QWBy2hKw0yo0d/view?usp=drive_link | Chrome